## UserStories
19
StoryID | Priority | Category | Story
W1 | 1 | World | As a the world, I want to be bounded so that actors can not move off the screen.
W2 | 1 | World | As the world, I want to add five pieces each to the two starting sides at the beginning of the game.
W3 | 1 | World | As the world, I want to add a row of tunnels to the top and bottom of the board (world)
W4 | 3 | World | As a world, I want to end the game when all of one player's checkers are "eaten"
W5 | 2 | World | As a world, I want to add mushrooms to the board after a random ammount of turns
W6 | 2 | World | As a World, I want to add bombs to the board after a random number of turns
W7 | 1 | World | As a world, I want to be able to know which player's turn it is
C1 | 2 | Checkers | As a checker, I want to know which team I'm on and set my image accordingly
C2 | 1 | Checkers | As a checker, I want to only be able to move diagonally unless I've been kinged
C3 | 2 | Checkers | As a checker, I want to "eat" the opposing pieces I jump over.
C4 | 3 | Checkers | As a checker, I want to be "kinged" when I jump through a tunnel
C5 | 2 | Checkers | As a checker, I want to make a sound when I jump another checker
C6 | 2 | Checkers | As a checker, I only want to be able to move when it's my player's turn
C7 | 1 | Checkers | As a checker, I want to be able to be dragged by the mouse to a new (legal) position
K1 | 3 | Kinged Checker | As a kinged checker, I want to be able to move any direction
M1 | 2 | Mushroom | As a mushroom, I want to king checkers that land on me.
B1 | 1 | Bomb | As a bomb, I want to remove from the board checkers that land on me
T1 | 3 | Tunnel | As a tunnel, I want to move checkers that land on me to the opposite side of the board
T2 | 3 | Tunnel | As a tunnel, I want to make a sound when a checker passes through me.

## ScrumBoard
12 | 2 | 0 | 5 | 19
To Do | In Progress | To verify | Done | Owner
|  |  | W1 | Lesli
|  |  | W2 | Hannah
|  |  | W2 | Hannah
W4
W5
W6
| W7 |  |  | Matt
C1
| C2 |  |  | Brandon
C3
C4
C5
C6
|  |  | C7 | Brandon
K1
M1
|  |  | B1 | Brandon
T1
T2

## Charts
To Do | 12 | 63.16%
In Progress | 2 | 10.53%
To verify | 0 | 0%
Done | 5 | 26.32%
Total | 19